## Sheet1
Wolfeboro Dockside Docks - Funding/Schedule Updated 1-6-2021
Revised Bid from Chesterfield 1/5/21 | Phase 1: Rebuild Dock A | Phase 2: Rebuild Docks B, C, & D | Phase 2: Rebuild Docks E,F,G &H | Total Phase 2 | Phase 3: Extend Docks B,C, D & E
Construction | 126657 | 391261 | 342240 | 733501 | 266000
Engineering | 6332.85 |  |  | 29340.04 | 15960
Electrical | 2000 |  |  | 20000 | 10000
Contingencies | 2000 |  |  | 67159 | 8040 | Total of all Phases
| 136989.85 |  |  | 850000.04 | 300000 | 1286989.89
Schedule | Complete by March 15 | Complete Docks B & C by 6-1-2021 | Complete remaining Docks by 3-1-2022 |  | Complete dock extensions by 5-15-22
Funding | WA 17- 2020 |  |  | New WA 2021 (bond) | Separate New WA 2021 (cash)